## Sheet1
GreenSwap/ King Corneil Kiaku - B00160936, Brevin Monks - B00162915, Jake Howe - B00164837
Date: | 2025-03-07 | Location:
Time: | 11am | F208
Chaired by | King
Attendees: | King & Brevin | Jake(Apologies sent)
Preparation for Meeting
Proposal written
Requirements analysis carried out
I | Open Meeting
To discuss the current state of the project
discuss soft Eng. and web server CA
II | Action Items from Previous Meeting | Responsible | Due Date
1 | Almost completed the structure of PHP which will act as a base | Jake | 2025-10-03
2 | Database has been completed which will be used in multiple pages | Brevin | 2025-12-03
3
III | Agenda Topic | Presenter | Duration | Minutes of the meeting
1 | Sign in Page | King | 16 minutes | King will continue the Sign up page
2 | Log in Page | Brevin | 14 minutes | Brevin will start the log in page
3 | PHP | King | 13 minutes | Jake is to figure out how to connect website to PHP
4 | Database connections | Jake | 13 minutes | Jake is to figure out how to connect the databases
5
5
IV | Close Meeting